## Sheet1
Название проекта
Менеджер проекта
Конечный результат проекта
Дата начала
Срок выполнения
Общий прогресс
Task | Priority | Hours | Status | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27
Week 1
Build model of engineering design process, determine where digital ConOps could deliver the value. | 3 | 1 | done
Determine the set of functionality for prototype | 3 | 2 | Done
Determine the requirements for Digital ConOps as a service. | 2 | 1,5 | Done
Determine set of tools for software implementation (gatsby, strapi, react ...). | 2 | 0,1 | done
Determine the project feasibility with a given timescale and resources (320 labor/hours) | 2 | 0,1 | done
Breakdown the work | 3 | 0,5 | done
Build week plan, fill Gantt chart, determine priorities | 3 | 1 | done
Determine risks | 2 | 0,5 | done
Read PM book | 1 | 1
Week 2
Develop information model for Digital ConOps (entities, relations..) | 3 |  | Done
Build a formal stakeholder model | 3 |  | Done
Present first result on SELT meeting, get feedback | 2 |  | Done
Update the requirements | 2 |  | Done
Update set of tools for realization (probably supervisor advise needed) | 2 |  | Done
Update feasibility | 2 |  | Done
Week 3
Improve Informational model | 3 |  | Done
Quick start with defined tools, create first training examples (full planned stack) | 3 |  | done
Present result on SELT meeting, get feedback | 2 |  | Done
Provide the methodology for requirement derivation from the client | 2 |  | Canceled
Collect required knowledge for the methodology and and provide library system for those data (wiki) | 2 |  | Canceled
Week 4
Fill the content in strapi | 2 |  | Late (1)
Impelemnt inf.model. In strapi | 3 |  | done
Design and implement pages layout | 3 |  | late (1)
Plot content from strapi backend according to developed scheme. Stakeholder, Needs, problems, potential solutions, and Conops description shall be implemented | 3 |  | Late (1)
Week 5
To make a display of a potential solution according to a new concept (focus on the intended elements of effectiveness) | 3 |  | done
CI/CD pipeline implementation | 2 |  | moved
Git course | 1
Fill the inf model with DR | 3 |  | done
Elastic search implementation | 1 |  | moved
Read and exract useful information from IEEE 29148 | 2 |  | done
Week 6
Study NGINX as an instrument | 1 |  | moved
Update UX/UI according to new iteration | 3 |  | done
Elastic search implementation | 1 |  | cancled
CI/CD pipeline implementation | 2 |  | moved
Week 7
Study NGINX as an instrument | 1 |  | canceled
create Chat bot prototype using google docs | 3 |  | canceled
CI/CD pipeline implementation | 3 |  | done
Week 8
Present idea to D. Kulish | 2
Collect feedback about notion conops | 3
Prepere pptx poster | 3
Improve ConOps according to feedback | 2